## Sprint 1
|  |  |  | Week #1 (7.5 hrs / week) |  |  |  |  | Week #2 (7.5 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 16 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11
|  |  |  | 2014-03-21 | 2014-03-22 | 2014-03-23 | 2014-03-24 | 2014-03-25 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02
|  |  |  | 60 | 54 | 48 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0 | Ideal Burndown
|  |  | 60 | 60 | 55 | 51 | 49 | 43 | 37 | 30 | 24 | 13 | 6 | -8 | Remaining Hrs (Total)
None - First Spring | System Architecture Design | Jayam | 6 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 0
| UML Diagrams | Prithvi | 6 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2 | 2 | 2 | 0
| Database Design | Ishan | 6 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 2 | 0 | 2 | 0
| Front end UI Wireframes | Pratyush | 6 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 2 | 0
| Literature Survey - Analyse other applications | Whole team | 12 | 2 | 0 | 0 | 1 | 2 | 0 | 1 | 2 | 2 | 2 | 0
| Study about Python - Flask | Whole team | 12 | 1 | 1 | 0 | 1 | 1 | 2 | 2 | 2 | 1 | 2
| Finalise designs after meetings | Whole team | 12 | 0 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 0
Team:
Ishan | 7.5 hours / Week
Jayam | 7.5 hours / Week
Pratyush | 7.5 hours / Week
Prithvi | 7.5 hours / Week
Total Available Hours During Sprint: | 60

## Sprint 2
|  |  |  | Week #1 (7.5 hrs / week) |  |  |  |  | Week #2 (7.5 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 16 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11
|  |  |  | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-16
|  |  |  | 60 | 54 | 48 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0 | Ideal Burndown
|  |  | 60 | 60 | 54 | 46 | 39 | 34 | 32 | 27 | 24 | 18 | 13 | 9 | Remaining Hrs (Total)
Front end UI Wireframes, Finalise design after meetings | System setup environment packages for backend | Whole team | 4 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Work on module hotel (business logic) | Jayam | 13 | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 0 | 1 | 0
| Work on module user (business logic) | Pratyush | 13 | 1 | 0 | 3 | 1 | 0 | 2 | 1 | 1 | 1 | 1 | 0
| Work on module rooms (business logic) | Ishan | 13 | 1 | 2 | 1 | 1 | 1 | 1 | 0 | 1 | 2 | 1 | 0
| Work on module booking (business logic) | Prithvi | 13 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 1
| Front end UI Wireframes | Pratyush | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Finalise designs | Whole team | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team:
Ishan | 7.5 hours / Week
Jayam | 7.5 hours / Week
Pratyush | 7.5 hours / Week
Prithvi | 7.5 hours / Week
Total Available Hours During Sprint: | 60

## Sprint 3
|  |  |  | Week #1 (7.5 hrs / week) |  |  |  |  | Week #2 (7.5 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 16 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11
|  |  |  | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | Ideal Burndown
|  |  |  | 60 | 54 | 48 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0 | Remaining Hrs (Total)
|  |  | 60 | 60 | 53 | 44 | 37 | 29 | 27 | 20 | 15 | 8 | 3 | -3
None | System setup environment packages for front end | Whole team | 4 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Finish Work on module hotel (create APIs) | Jayam | 10 | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 0 | 1 | 0
| Finish Work on module user (create APIs) | Pratyush | 10 | 1 | 0 | 3 | 1 | 0 | 2 | 1 | 1 | 1 | 1 | 0
| Finsh Work on module rooms (create APIs) | Ishan | 10 | 1 | 2 | 1 | 1 | 1 | 1 | 0 | 1 | 2 | 1 | 0
| Finish Work on module booking (create APIs) | Prithvi | 10 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 1
| Finalise front end designs | Whole team | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test integrated APIs | Whole team | 14 | 2 | 2 | 0 | 3 | 0 | 2 | 2 | 1 | 0 | 2 | 0
Team:
Ishan | 7.5 hours / Week
Jayam | 7.5 hours / Week
Pratyush | 7.5 hours / Week
Prithvi | 7.5 hours / Week
Total Available Hours During Sprint: | 60

## Sprint 4
|  |  |  | Week #1 (7.5 hrs / week) |  |  |  |  | Week #2 (7.5 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 16 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11
|  |  |  | 2014-03-21 | 2014-03-22 | 2014-03-23 | 2014-03-24 | 2014-03-25 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02
|  |  |  | 60 | 54 | 48 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0
|  |  | 60 | 60 | 55 | 48 | 41 | 35 | 33 | 30 | 26 | 13 | -1 | -1
Front end designs | Complete the login sign up front end flow | Ishan | 10 | 1 | 2 | 1 | 0 | 0 | 0 | 2 | 3 | 3 | 0 | 0
| Complete the booking front end flow | Jayam | 13 | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 3 | 0 | 0
| Complete the admin front end flow | Pratyush | 8 | 1 | 1 | 3 | 1 | 0 | 2 | 1 | 1 | 1 | 0 | 0
| Integrate and test | Whole team | 8 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 0 | 0
| Dry run on development server | Whole team | 10 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0
| Fix the remaining bugs | Whole team | 8 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 0
| Finalise and deploy on server | Jayam | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0
Team:
Ishan | 7.5 hours / Week
Jayam | 7.5 hours / Week
Pratyush | 7.5 hours / Week
Prithvi | 7.5 hours / Week
Total Available Hours During Sprint: | 60